{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["技术团队工作分解","关键用户小组工作分解"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"技术团队工作分解","index":0,"n_rows":36,"n_cols":9,"rows_kept":36,"cut":false,"hidden":false,"merged":[[1,2,1,8],[26,1,27,1]]}
[]
[null,"板块","明确事项"]
[null,"demo开发（2019/9/15结束）","功能","模型开发责任人","  模型开发时间（完成时间）","数据源来源 ","数据集","数据集责任人 ","数据集ok时间"]
[null,null,"货代看板","张悦","2019-09-07","k3凭证、wms系统作业明细、库存明细、lfs系统货代板块","货代相关数据集","张悦","2019-09-22"]
[null,null,"船代看板","张悦","2019-09-09","k3凭证、lfs系统船代板块、excel数据源","船代相关数据集","张悦","2019-09-30"]
[null,null,"运输看板","李少进","2019-09-11","k3凭证、lfs系统货代板块、excel数据源","运输相关数据集","李少进","2019-09-22"]
[null,null,"仓储看板","孙康","2019-09-11","k3凭证、lfs系统仓储板块、excel数据源、wms系统库存作业费用明细","仓储相关数据集","孙康","2019-09-22"]
[null,null,"市场看板","李少进","2019-09-13","k3凭证、lfs系统板块、excel数据源、wms系统库存作业费用明细","市场相关数据集","李少进","2019-09-28"]
[null,null,"人力资源看板","孙康","2019-09-13","excel数据源","人力资源相关数据集","孙康","2019-09-30"]
[null,null,"财务看板","孙康","2019-09-15","k3凭证、lfs系统板块、wms系统费用明细","财务相关数据集","孙康","2019-09-30"]
[null,null,"客户看板","李少进","2019-09-15","k3凭证、lfs系统板块、excel数据源、wms系统库存作业费用明细","客户相关数据集","李少进","2019-09-30"]
[]
[null,"数据资源整合（2019/10/8结束）","数据仓库主题","数据仓库板块设计","取数ETL负责人","业务系统取数负责人","数据仓库完成时间"]
[null,null,"18年维度数据","李少进","孙康","黄国伟","2019-09-28"]
[null,null,"19年之后的数据","李少进","孙康","黄国伟","2019-09-28"]
[null,null,"仓储库存明细","李少进","孙康","肖得志","2019-09-28"]
[null,null,"仓储作业明细","李少进","孙康","肖得志","2019-09-28"]
[null,null,"仓储费用明细","李少进","孙康","肖得志","2019-09-28"]
[null,null,"LFS数据货代板块","李少进","孙康","张宇航","2019-09-22"]
[null,null,"LFS数据船代板块","李少进","孙康","张宇航","2019-09-22"]
[null,null,"LFS数据仓储板块","李少进","孙康","张宇航","2019-09-22"]
[null,null,"LFS数据运输板块","李少进","孙康","张宇航","2019-09-22"]
[]
[]
[]
[null,"主题看板开发（2019/10/31结束）","功能","看板开发责任人","数据集ok时间（demo优化开始时间）","看板开发时间（完成时间）"]
[null,"将demo优化成正式主题看板，在相应数据集准备完成后","货代看板","张悦","2019-09-22","2019-09-30"]
[null,null,"船代看板","张悦","2019-09-30","2019-10-31"]
[null,null,"运输看板","李少进","2019-09-22","2019-09-30"]
[null,null,"仓储看板","孙康","2019-09-22","2019-09-30"]
[null,null,"市场看板","李少进","2019-09-28","2019-10-20"]
[null,null,"人力资源看板","孙康","2019-09-30","2019-10-31"]
[null,null,"财务看板","孙康","2019-09-30","2019-10-31"]
[null,null,"客户看板","李少进","2019-09-30","2019-10-31"]
[]
[null,"自助分析报表（关键用户小组）"]

{"sheet":"关键用户小组工作分解","index":1,"n_rows":23,"n_cols":7,"rows_kept":23,"cut":false,"hidden":false,"merged":[[1,2,1,6],[13,1,14,1],[3,5,10,5]]}
[]
[null,"阶段","明确事项"]
[null,"demo开发（2019/9/15结束）","功能","模型开发负责人","  模型开发时间（完成时间）","模型优化沟通","数据集ok时间"]
[null,null,"货代看板","张悦","2019-09-09","指标展示布局\n指标分析纬度\n指标的计算公式","2019-09-22"]
[null,null,"船代看板","张悦","2019-09-15",null,"2019-09-30"]
[null,null,"运输看板","李少进","2019-09-11",null,"2019-09-22"]
[null,null,"仓储看板","孙康","2019-09-11",null,"2019-09-22"]
[null,null,"市场看板","李少进","2019-09-13",null,"2019-09-28"]
[null,null,"人力资源看板","孙康","2019-09-13",null,"2019-09-30"]
[null,null,"财务看板","孙康","2019-09-15",null,"2019-09-30"]
[null,null,"客户看板","李少进","2019-09-15",null,"2019-09-30"]
[]
[null,"主题看板开发（2019/10/31结束）","功能","看板开发责任人","数据集ok时间（demo优化开始时间）","看板开发完成、用户测试时间"]
[null,"将demo优化成正式主题看板，在相应数据集准备完成后","货代看板","张悦","2019-09-22","2019-09-30"]
[null,null,"船代看板","张悦","2019-09-30","2019-10-31"]
[null,null,"运输看板","李少进","2019-09-22","2019-09-30"]
[null,null,"仓储看板","孙康","2019-09-22","2019-09-30"]
[null,null,"市场看板","李少进","2019-09-28","2019-10-20"]
[null,null,"人力资源看板","孙康","2019-09-30","2019-10-31"]
[null,null,"财务看板","孙康","2019-09-30","2019-10-31"]
[null,null,"客户看板","李少进","2019-09-30","2019-10-31"]
[]
[null,"自助分析报表（关键用户小组）","2019/9/30之后"]